## Slide 1
Project Management
MGT 30725
  Indike Manthilake MBA, Msc, Bsc, CSM, PMI-ACP
  indikem@gmail.com

## Slide 2
Agenda
PERT and Critical Path Analysis
Lesson 6 – The Project Schedule

## Slide 3
Precedence Diagramming Method (PDM)
Activity-on-Node (AON) Diagramming Method
Method used in Critical Path Methodology (CPM)
No dummy activities
Activities are represented by boxes
Arrows show relationships between activities
Very popular and used by project management software
Better at showing different types of dependencies
PERT (Program Evaluation Review Technique)

## Slide 4
Leads and Lags
Use leads and lags to support realistic and achievable project schedule.
Each activity is connected at least to one predecessor and one successor except the start and the end.
A
B
C
predecessor
Successor
Leads
May be added to start an activity before the predecessor activity is complete.
A
B
Lags
Inserted waiting time between activities
A
B
Sequence activities

## Slide 5
FS – 2 days
A100 FOUNDATIONS
A400 PLUMBING
A400 - LEAD (Acceleration) by 2 days
Leads and Lags
FS + 2 days
A100 WALL PAINTING COAT1
A200 - LAG (Delayed) by 2 days (need to allow Coat1 painting to dry first before applying Coat2)
A200 WALL PAINTING
COAT2
Sequence activities

## Slide 6
Project Schedule Network Diagrams
Graphical representation of the logical relationships, also referred to as dependencies, among the project schedule activities
Network diagram is produced manually or by using project management software.
Sequence activities

## Slide 7
Exercise: Draw an AON Network for the following precedence table
Network Diagrams – Activity on Node (AON)

## Slide 8
A
B
C
E
D
F
Start
Finish
Network Diagrams – Activity on Node (AON)

## Slide 9
Preceding Activity | Succeeding Activity
Start | A100
A100 | A200
A100 | A300
A200 | A400
A300 | A500
A400 | A600
A500 | A600
A600 | Finish
Draw a network diagram based on the above table
Network Diagrams – Exercise 1

## Slide 10
Network Diagrams – Exercise 2

## Slide 11
Network Diagrams – Exercise 2

## Slide 12
LS
Float
LF
ES
DUR
EF
Task ID
ES – Early Start
EF – Early Finish
LS – Late Start
LF – Late Finish
DUR - Duration
Network Diagrams

## Slide 13
One Predecessor
  Early Start (ES) = EFp
        ES = 3
  Early Finish (EF) = Early Start (ES) + Duration
  EF = 3 + 4 = 7
A100 (Task 1) FOUNDATIONS
A200 (Task 2) WALLS
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
ES
EF
ES
EF
LS
Float
LF
ES
DUR
EF
Task ID
Network Diagrams – Forward Pass

## Slide 14
Multiple Predecessor
  Early Start (ES) = Max(EFp)
  ES = 3
      last completion date of all predecessors
A300
A400
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
ES
EF
ES
EF
LS
Float
LF
ES
DUR
EF
Task ID
A200
ES
EF
A100
ES
EF
Network Diagrams – Forward Pass

## Slide 15
LS
Float
LF
0
3
3
A100
LS
Float
LF
3
4
7
A200
FS
Finish-to-Start
LS
Float
LF
ES
DUR
EF
Task ID
A100 (Task 1) FOUNDATIONS
A200 (Task 2) WALLS
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
ES
EF
ES
EF
Network Diagrams – Forward Pass

## Slide 16
One Successor
  Late Finish(LF) = LSs
  LF = 3
  Late Start(LS) = Late Finish(LF) – Duration
  LS = 3 - 3 = 0
LS
Float
LF
ES
DUR
EF
Task ID
A100 (Task 1) FOUNDATIONS
A200 (Task 2) WALLS
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
LS
LF
LS
LF
Network Diagrams – Backward Pass

## Slide 17
Multiple Successor
  Late Finish (LF) = Min(LSs)
  LF = 4
      earliest completion all successors
LS
Float
LF
ES
DUR
EF
Task ID
A300
A200 (Task 2) WALLS
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
LS
LF
LS
LF
A200
LS
LF
A100
LS
LF
Network Diagrams – Backward Pass

## Slide 18
LS
Float
LF
ES
DUR
EF
Task ID
0
Float
3
0
3
3
A100
3
Float
7
3
4
7
A200
FS
Finish-to-Start
A100 (Task 1) FOUNDATIONS
A200 (Task 2) WALLS
May 1
May 2
May 3
May 4
May 5
May 6
May 7
May 8
LS
LF
LS
LF
Network Diagrams – Backward Pass

## Slide 19
Float = Late Start – Early Start
0
0
3
0
3
3
A100
3
0
7
3
4
7
A200
FS
Finish-to-Start
LS
Float
LF
ES
DUR
EF
Task ID
Network Diagrams – Float/Slack

## Slide 20
Critical Path is the longest duration path in a Network Diagram.
IT identifies the shortest time needed to complete a project.
There can be more than one critical path in a Network Diagram.
Near-critical path is the path that has close in duration to critical path.
Any delay to an activity in a Critical Path will delay the entire project.
All activities in a Critical Path contains zero (0) slack/float.
Critical Path Method (CPM)

## Slide 21
Following activities were identified as main tasks for the computerization project. Draw the Activity on Node (AON) network diagram and mark the critical path for the project.
TaskID | Activity | Time (weeks) | Immediate predecessor
A | Analyse Requirements | 6 | ----
B | System Design | 8 | A
C | Finalyse the Architecture | 4 | A
D | Database Design | 6 | B
E | System Implementation | 6 | D
F | Testing | 8 | E
G | UAT | 12 | F
H | Parallel Run | 4 | G
I | Rollout | 1 | C,H
Case Study - 1

## Slide 22
Used to shorten the schedule duration without reducing the project scope.
Crashing - used to shorten the schedule duration for the least incremental cost by adding resources. Examples of crashing include approving overtime, bringing in additional resources, or paying to expedite delivery to activities on the critical path. Crashing works only for activities on the critical path where additional resources will shorten the activity’s duration.
Fast Tracking - activities or phases normally done in sequence are performed in parallel for at least a portion of their duration. An example is constructing the foundation for a building before completing all of the architectural drawings.
Schedule Compression

## Slide 23
Refer ABC superMKT case study and answer questions
Group Work - Case Study - 2
Expected Duration - Exercise

## Slide 24
Agenda
Estimate Costs and income
Creating a Preliminary Budget
Budget and Schedule Balancing
Lesson 7 – The Project Schedule